## Sheet1
Module | Man Day for 2 developers ( Primary estimation)
1. Code Review & Reformat | 40
2. Authentication | 10 | Total Man Day for 2 developers | 170
3. Authorization | 20
4. User Management | 10
5.Audit Log | 10
6. Approval flow | 20
7. Company management | 30
9. UI fix | 20
10. Admin Dash board | 20
Buffer | 30
1. Custom Workflow | 30
2. Report Management | 30
3. Report page through email link | 20
4. Activities | 10
8. Dynamic Form Management | 25
1. Data parse with ai | 20
2. Recommendation system | 10
3. Collaboration with odms | 20
4. Import based features | Requirement analysis yet to be done